## Product_Process_Matrix
|  |  | Project Brief | Project Initiation Document | Project Plan | Stage Plan | Business Case | Issue Log | Quality Log | Communication Plan | Risk Log | Configuration Item Record
Starting a Project | SU4 | Preparing a Project Brief | C |  |  |  | C |  |  |  | C
| SU5 | Defining Project Approach | I | [7 empty] | I
| SU6 | Planing an Initiation Stage | I |  |  | C |  |  |  |  | U
Initiating a Project | IP1 | Planning Quality | I | [5 empty] | C
| IP2 | Planning a Project | I |  | C | [5 empty] | U
| IP3 | Refining Business Case and Risks | I |  | U |  | U |  |  |  | U
| IP4 | Setting up Project Control |  |  | U |  |  |  |  | C | U
| IP5 | Setting Up Project Files |  |  | I |  |  | C
| IP6 | Assembling a Project Initiation Document | I | C | I |  | I |  |  | I | I
Directing a Project | DP1 | Authorising Initiation | I |  |  | I |  |  |  |  | I
| DP2 | Authorising a Project |  | I |  | I
| DP3 | Autorising Stage and Exception Plan |  | I | I | I | I |  |  |  | I
| DP4 | Giving ad hoc Direction | [5 empty] | U |  | I
| DP5 | Confirming Project Closure |  | I | [5 empty] | I
Controlling a Stage | CS1 | Authorising Work Package |  |  |  | U |  | U | U |  | U | U
| CS2 | Assessing Progress |  |  |  | U |  | U | I |  |  | U
| CS3 | Capturing Project Issues | [5 empty] | U
| CS4 | Examining Project Issues |  |  | I | I | I | U |  |  | U
| CS5 | Reviewing Stage Status |  |  | I | I | I | I | I |  | I | I
| CS6 | Reporting Highlights |  |  |  | I |  | I | I | I | I
| CS7 | Taking Corrective Action |  |  |  | I |  | U |  |  | U | U
| CS8 | Escalating Project Issues |  | I | I | I | I | U |  |  | I | U
| CS9 | Receiving Completed Work Packages | [6 empty] | I |  |  | U
Managing Product Delivery | MP1 | Accepting a Work Package | [6 empty] | U |  | U
| MP2 | Executing a Work Package | [6 empty] | U
| MP3 | Delivering a Work Package | [6 empty] | I
Managing Stage Boundaries | SB1 | Planning a Stage |  | I | I | C |  | I | U |  | U
| SB2 | Updating a Project Plan |  |  | U | I |  | U |  |  | U
| SB3 | Updating a Project Business Case |  |  | I |  | U | U |  |  | U
| SB4 | Updating the Risk Log |  |  | U |  | I | U |  |  | U
| SB5 | Reporting Stage End |  |  |  | I | I | I | I | U | I | U
| SB6 | Producing an Exception Plan |  | I | I | I |  | I | U |  | I
Closing a Project | CP1 | Decommissioning a Project |  | I |  |  |  | I |  | I |  | I
| CP2 | Identifying follow-on Actions |  |  |  |  | I | I |  |  | I
| CP3 | Project Evaluation Review |  | I | U |  | I | I | I |  | I | I
Planning | PL1 | Designing a Plan | I | I
| PL2 | Defining and Analysing Products | [9 empty] | C
| PL3 | Identifying Activities and Dependencies | [8 empty] | I
| PL4 | Estimating
| PL5 | Scheduling
| PL6 | Analysing Risks | [8 empty] | U
| PL7 | Completing a Plan |  |  | C | C